## Info
Leonora Cost Plan - Converted Spreadsheet
Document | Indicative Cost Plan
Project | Horizon Construction : Leonora (Blocks A - E)
Author | Duncan Hay / Cubix Construction Consultants
Date | 11-Mar-26
Converted from | 26-01-28 Leonora CP Rev C (Blocks A - E).pdf
Source note | Converted into editable workbook from PDF text and tables. Values are transcribed from the uploaded PDF; formulas added for key subtotal/total rows where applicable.

## Executive Summary
Executive Summary
Item | Block A | Block B | Block C | Block D | Block E | Total
Nr of Units | 6 | 9 | 9 | 3 | 4 | 31
Substructure | 53300 | 72800 | 72800 | 32000 | 47000 | 277900
Superstructure | 297000 | 379700 | 368400 | 167100 | 176900 | 1389100
Internal Finishes | 70600 | 106400 | 106400 | 41100 | 44400 | 368900
Fixture and Furnishings | 49800 | 74400 | 73800 | 27000 | 32800 | 257800
Services | 153465 | 232216 | 232216 | 83842 | 102718 | 804457
Build Cost Subtotal | 624165 | 865516 | 853616 | 351042 | 403818 | 3098157
Preliminaries | 99866 | 138482 | 136578 | 56167 | 64611 | 495704
Block Cost Total | 724031 | 1003998 | 990194 | 407209 | 468429 | 3593861
External Works - Blocks A-E | [5 empty] | 619308
External Works - Site Wide Works | [5 empty] | 237900
External Works Total | [5 empty] | 857208
Sub-Total | [5 empty] | 4451069
Risk & OH&P | [5 empty] | 517802
Subtotal incl Risk/OH&P | [5 empty] | 4968871
Statutory Authority Charges | [5 empty] | 100000
Renewables | [5 empty] | 64800
Site Clearance / Demolition | [5 empty] | 125000
Forecast Net Construction Cost / Unit | [5 empty] | 5258671
Project Contingency @ 7.5% | [5 empty] | 394400
Inflation | [5 empty] | Excluded
Project Financing | [5 empty] | Excluded
Forecast Net Construction Cost (Say) | [5 empty] | 5653071
S106 Works / CIL contribution | [5 empty] | Excluded
Professional Fees / On costs @ 10% | [5 empty] | Excluded
Zurich/NHBC Fee | [5 empty] | Excluded
Surveys / Site Investigations | [5 empty] | 25000
Total Net Project Cost excl VAT | [5 empty] | 5678071

## Area Schedule
Schedule of Residential Accommodation
Floor | Block A m2 | Block A ft2 | Block B m2 | Block B ft2 | Block C m2 | Block C ft2 | Block D m2 | Block D ft2 | Block E m2 | Block E ft2
Ground Floor | 135 | 1452 | 200 | 2153 | 200 | 2153 | 80 | 862 | 130 | 1399
First Floor | 135 | 1452 | 200 | 2153 | 200 | 2153 | 80 | 862 | 130 | 1399
Second Floor | 118 | 1272 | 200 | 2153 | 200 | 2153 | 59 | 639
Sub-Total | 388 | 4177 | 600 | 6458 | 600 | 6458 | 220 | 2363 | 260 | 2799
Nr of units | 6 | Nr | 9 | Nr | 9 | Nr | 3 | Nr | 4 | Nr

## Elemental Costs
Breakdown of Elemental Costs
Ref | Element | A Cost | A £/m² | B Cost | B £/m² | C Cost | C £/m² | D Cost | D £/m² | E Cost | E £/m² | Notes
1 | 1 Substructure | 53300 | 137 | 72800 | 121 | 72800 | 121 | 32000 | 146 | 47000 | 181
2 | 2A Frame / Upper floors | 37000 | 95 | 58400 | 97 | 58400 | 97 | 20400 | 93 | 19000 | 73
3 | 2C Roof | 66300 | 171 | 88200 | 147 | 101500 | 169 | 47200 | 215 | 36500 | 140
4 | 2D Stairs | 9600 | 25 | 9600 | 16 | 9600 | 16 | 9600 | 44 | 3600 | 14
5 | 2E External Walls | 100700 | 260 | 99400 | 166 | 72900 | 122 | 43500 | 198 | 57000 | 219
6 | 2F Windows & External Door | 20700 | 53 | 24100 | 40 | 25900 | 43 | 12500 | 57 | 20900 | 80
7 | 2G Internal Walls/Partitions | 42100 | 108 | 62700 | 105 | 62800 | 105 | 23400 | 107 | 31600 | 122
8 | 2H Internal Doors | 20600 | 53 | 37300 | 62 | 37300 | 62 | 10500 | 48 | 8300 | 32
9 | 3A Wall Finishes | 30200 | 78 | 44000 | 73 | 44000 | 73 | 18000 | 82 | 21700 | 83
10 | 3B Floor Finishes | 22400 | 58 | 34500 | 58 | 34500 | 58 | 12900 | 59 | 10600 | 41
11 | 3C Ceiling Finishes | 18000 | 46 | 27900 | 47 | 27900 | 47 | 10200 | 46 | 12100 | 47
12 | 4 Fittings & Furnishings | 49800 | 128 | 74400 | 124 | 73800 | 123 | 27000 | 123 | 32800 | 126
13 | 5 Services | 153465 | 395 | 232216 | 387 | 232216 | 387 | 83842 | 382 | 102718 | 395
| Sub Total | 624165 | 1609 | 865516 | 1443 | 853616 | 1423 | 351042 | 1599 | 403818 | 1553
15 | 7 Main Contractor Preliminaries | 99866 | 257 | 138482 | 231 | 136578 | 228 | 56167 | 256 | 64611 | 249
16 | 8 Main Contractor Risk (2.5%) | 18101 | 47 | 25100 | 42 | 24755 | 41 | 10180 | 46 | 11711 | 45
17 | 9 Main Contractors OH&P (7%) | 51949 | 134 | 72037 | 120 | 71046 | 118 | 29217 | 133 | 33610 | 129
| Total | 794081 | 2046 | 1101135 | 1835 | 1085995 | 1810 | 446606 | 2034 | 513749 | 1976

## 1 Substructure
1 Substructure
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Excavation to reduce levels; disposal off site | m2 | 20 | 135 | 2699 | 200 | 4000 | 200 | 4000 | 80 | 1602 | 130 | 2600
2 | Piling | Nr | 480 | N/A |  | N/A |  | N/A |  | N/A |  | N/A
3 | Pile caps | Nr | 950 | N/A |  | N/A |  | N/A |  | N/A |  | N/A
4 | Trench footings | m | 375 | 76 | 28500 | 96 | 36000 | 96 | 36000 | 46 | 17250 | 62 | 23063
5 | Beam / block flooring | m2 | 130 | 135 | 17541 | 200 | 26000 | 200 | 26000 | 80 | 10410 | 130 | 16900
6 | Screed / topping | m2 | 34 | 135 | 4588 | 200 | 6800 | 200 | 6800 | 80 | 2723 | 130 | 4420
| Package Total |  |  |  | 53327 |  | 72800 |  | 72800 |  | 31985 |  | 46983
| To Summary |  |  |  | 53300 |  | 72800 |  | 72800 |  | 32000 |  | 47000

## 2A Frame Upper Floors
2A Super-structure / Upper floors
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Upper floors to apartment | m2 | 146 | 253 | 36954 | 400 | 58400 | 400 | 58400 | 139 | 20364 | 130 | 18980
2 | Ditto to houses | m2 | 86
| Package Total |  |  |  | 36954 |  | 58400 |  | 58400 |  | 20364 |  | 18980
| To Summary |  |  |  | 37000 |  | 58400 |  | 58400 |  | 20400 |  | 19000

## 2C Roof
2C Roof
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Pitched roof covering incl structure | m2 | 190 | 258 | 49020 | 371 | 70490 | 407 | 77330 | 149 | 28348 | 176 | 33345
2 | Rainwater downpipes, gutters and the like | m | 42 | 76 | 3192 | 74 | 3108 | 74 | 3108 | 67 | 2814 | 76 | 3192
3 | Velux roof lights | Nr | 850 | 2 | 1700 | N/A |  | 5 | 4250 | N/A |  | N/A
4 | Allowance to form dormer windows | Nr | 2200 | 4 | 8800 | 5 | 11000 | 6 | 13200 | 4 | 8800 | N/A
5 | Porch roof | It | 3600 | 1 | 3600 | 1 | 3600 | 1 | 3600 | 2 | 7200
| Package Total |  |  |  | 66312 |  | 88198 |  | 101488 |  | 47162 |  | 36537
| To Summary |  |  |  | 66300 |  | 88200 |  | 101500 |  | 47200 |  | 36500

## 2D Stairs
2D Stairs
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Communal stairs incl balustrade | Flts | 4800 | 2 | 9600 | 2 | 9600 | 2 | 9600 | 2 | 9600 |  |  | Rate inclusive of balustrade/handrail etc
2 | Internal stairs | Flts | 1800 | [7 empty] | 2 | 3600
| Package Total |  |  |  | 9600 |  | 9600 |  | 9600 |  | 9600 |  | 3600
| To Summary |  |  |  | 9600 |  | 9600 |  | 9600 |  | 9600 |  | 3600

## 2E External Walls
2E External Walls
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Block/feature stone cavity wall | m2 | 220 | 236 | 51998 |  |  |  |  | 132 | 28987
2 | Cavity block/render wall | m2 | 160 | 167 | 26775 | 428 | 68544 | 422 | 67451 | 154 | 24678
3 | EO feature bath stone banding | m | 180 | 122 | 21960 | 172 | 30888 | 30 | 5454 | 17 | 3024 | 19 | 3330
4 | Cavity brick/block wall | m2 | 160 | [6 empty] | 253 | 40464
| Package Total |  |  |  | 100733 |  | 99432 |  | 72905 |  | 43488 |  | 56996
| To Summary |  |  |  | 100700 |  | 99400 |  | 72900 |  | 43500 |  | 57000

## 2F Windows Doors
2F Windows / External Doors
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Window units 600 x 1000 | Nr | 276 | 4 | 1104 | 3 | 828 | 3 | 828 | 4 | 1104 |  |  | slim profile uPVC
| Window units 600 x 1400 | Nr | 386 | 4 | 1546
| Window units 1000 x 800 | Nr | 368 | [8 empty] | 7 | 2576
| Window units 1000 x 1200 | Nr | 552 | [8 empty] | 10 | 5520
| Window units 1200 x 1200 | Nr | 662 | 17 | 11261 | 18 | 11923 | 18 | 11923 | 13 | 8611
| Window units 1000 x 1500 | Nr | 690
| Window units 1200 x 1800 | Nr | 994 | [8 empty] | 6 | 5962
| Window units 1400 x 1800 | Nr | 994 | 4 | 3974 | 3 | 2981 | 4 | 3974
2 | Patio / French doors - Single | No | 1800 | N/A |  | 1 | 1800 | N/A |  | N/A
| Patio / French doors - Double | No | 2600 | N/A |  | 2 | 5200 | 3 | 7800 | N/A |  | 1 | 2600
3 | Secure entrance door | No | 1400 | 2 | 2800 | 1 | 1400 | 1 | 1400 | 2 | 2800 | 3 | 4200
| Package Total |  |  |  | 20685 |  | 24132 |  | 25926 |  | 12515 |  | 20858
| To Summary |  |  |  | 20700 |  | 24100 |  | 25900 |  | 12500 |  | 20900

## 2G Internal Partitions
2G Internal Partitions
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Internal Party Walls | lm | 230 | 42 | 9660 | 84 | 19320 | 84 | 19320 | 17 | 3910 | 26 | 5980 | Refer to Section 2E
2 | Internal plasterboard partitions; 2400 high | lm | 190 | 120 | 22705 | 174 | 33060 | 176 | 33345 | 71 | 13395 | 99 | 18715 | Rate inclusive of plaster skim finish
3 | Dry lining to external walls | m2 | 24 | 404 | 9689 | 428 | 10282 | 422 | 10118 | 253 | 6070 | 286 | 6864
| Package Total |  |  |  | 42054 |  | 62662 |  | 62783 |  | 23375 |  | 31559
| To Summary |  |  |  | 42100 |  | 62700 |  | 62800 |  | 23400 |  | 31600

## 2H Internal Doors
2H Internal Doors
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Apartment entrance doors | Nr | 950 | 6 | 5700 | 9 | 8550 | 9 | 8550 | 2 | 1900 | 2 | 1900 | Rate inclusive of labour, ironmongery, frame, architrave etc
2 | Internal single doors | Nr | 480 | 31 | 14880 | 48 | 23040 | 48 | 23040 | 18 | 8640 | 12 | 5760 | Rate inclusive of labour, ironmongery, frame, architrave etc
| Ditto double doors | Nr | 605 | [8 empty] | 1 | 605
3 | Communal Doors | Nr | 950 | N/A |  | 6 | 5700 | 6 | 5700 | N/A |  | N/A |  | Rate inclusive of labour, ironmongery, frame, architrave etc
| Package Total |  |  |  | 20580 |  | 37290 |  | 37290 |  | 10540 |  | 8265
| To Summary |  |  |  | 20600 |  | 37300 |  | 37300 |  | 10500 |  | 8300

## 3A Wall Finishes
3A Wall Finishes
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Emulsion paint finish to internal walls | m2 | 9 | 1308 | 11773 | 1873 | 16859 | 1875 | 16873 | 743 | 6686 | 983 | 8849 | Res
2 | Full height tiling to bathrooms/ensuites | m2 | 80 | 121 | 9677 | 181 | 14515 | 181 | 14515 | 81 | 6518 | 81 | 6451 | Res
3 | Tiling to splashbacks | m2 | 75 | 29 | 2160 | 43 | 3240 | 43 | 3240 | 14 | 1080 | 19 | 1440 | Res
4 | Gloss painted mdf skirtings | lm | 12 | 545 | 6541 | 781 | 9366 | 781 | 9374 | 310 | 3715 | 410 | 4916 | Res
| Package Total |  |  |  | 30150 |  | 43980 |  | 44002 |  | 17999 |  | 21656
| To Summary |  |  |  | 30200 |  | 44000 |  | 44000 |  | 18000 |  | 21700

## 3B Floor Finishes
3B Floor Finishes
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Carpet flooring inc underlay | m2 | 30 | 249 | 7483 | 404 | 12132 | 404 | 12132 | 134 | 4007 | 198 | 5952
2 | Non slip ceramic tile flooring | m2 | 80 | 26 | 2112 | 40 | 3168 | 40 | 3168 | 23 | 1824 | 18 | 1408
3 | Entrance matting incl framing etc | nr | 250 | 1 | 250 | 1 | 250 | 1 | 250 | 1 | 250 |  |  | Excl
4 | Engineered timber flooring to kitchen/dining area | m2 | 74 | 66 | 4884 | 99 | 7326 | 99 | 7326 | 33 | 2442 | 44 | 3256
5 | Provision of hard wearing finishes to communal areas | m2 | 35 | 46 | 1617 | 57 | 1995 | 57 | 1995 | 30 | 1057 | N/A
6 | Acoustic protection to floors | m2 | 24 | 253 | 6075 | 400 | 9600 | 400 | 9600 | 139 | 3348 | N/A
| Package Total |  |  |  | 22421 |  | 34471 |  | 34471 |  | 12927 |  | 10616
| To Summary |  |  |  | 22400 |  | 34500 |  | 34500 |  | 12900 |  | 10600

## 3C Ceiling Finishes
3C Ceiling Finishes
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Plasterboard ceilings | m2 | 38 | 388 | 14746 | 600 | 22800 | 600 | 22800 | 220 | 8343 | 260 | 9880 | Res
2 | Emulsion paint finish to ceilings | m2 | 8.5 | 388 | 3298 | 600 | 5100 | 600 | 5100 | 220 | 1866 | 260 | 2210 | Res
3 | Covings to ceilings |  |  | Excluded |  | Excluded |  | Excluded |  | Excluded |  | Excluded
| Package Total |  |  |  | 18044 |  | 27900 |  | 27900 |  | 10210 |  | 12090
| To Summary |  |  |  | 18000 |  | 27900 |  | 27900 |  | 10200 |  | 12100

## 4 Fixtures Fittings
4 Fixtures and Fittings
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Kitchen fit out excl. white goods etc - Apartments | Nr | 4800 | 6 | 28800 | 9 | 43200 | 9 | 43200 | 3 | 14400 | 4 | 19200
2 | Bathroom fit out (Sanitaryware etc) | Nr | 1900 | 6 | 11400 | 9 | 17100 | 9 | 17100 | 3 | 5700 | 4 | 7600 | Bath, shower/screen, WC, vanity unit, taps etc
3 | En-suite fit out | Nr | 1200 | N/A |  | N/A |  | N/A |  | 2 | 2400 | N/A |  | WC, WHB, shower/screen, vanity unit, taps etc
4 | WC fit out | Nr | 600 | 1 | 600 | 1 | 600 | N/A |  | N/A |  | N/A |  | WC, WHB, vanity unit mirror etc
5 | Utility room fit out | Nr | 2600 | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | Units / Sink etc
6 | Built in wardrobes | Nr | 1500 | N/A |  | N/A |  | N/A |  | N/A |  | N/A
7 | Allowance for forming cupboards / stores etc | Nr | 800 | 6 | 4800 | 9 | 7200 | 9 | 7200 | 3 | 2400 | 4 | 3200
8 | Sundry timber (Window boards / pattresses / noggins etc) | Nr | 700 | 6 | 4200 | 9 | 6300 | 9 | 6300 | 3 | 2100 | 4 | 2800
| Package Total |  |  |  | 49800 |  | 74400 |  | 73800 |  | 27000 |  | 32800
| To Summary |  |  |  | 49800 |  | 74400 |  | 73800 |  | 27000 |  | 32800

## 5 Services
5 Services Installation
Ref | Description | Unit | Rate | A Qty | A Total | B Qty | B Total | C Qty | C Total | D Qty | D Total | E Qty | E Total | Comments
1 | Sanitary fittings | m2 | Included elsewhere
2 | Soil waste stacks / Foul water disposal | Nr | 620 | 12 | 7440 | 18 | 11160 | 18 | 11160 | 9 | 5580 | 8 | 4960 | Allowance for bathroom/kitchen/en-suite
3 | Hot/cold water installation excl heat source - Apartments | Pts | 3240 | 6 | 19440 | 9 | 29160 | 9 | 29160 | 3 | 9720 | 4 | 12960
| Hot/cold water installation excl heat source - Houses | Pts | 3780
4 | Toilet, Kitchen & Bathroom extract / MVHR | Nr | 720 | 12 | 8640 | 18 | 12960 | 18 | 12960 | 9 | 6480 | 8 | 5760 | Kitchen, WC's and en-suites
5 | Heating / hot water system boiler - Apartments | Nr | 3000 | 6 | 18000 | 9 | 27000 | 9 | 27000 | 3 | 9000 | 4 | 12000
| Heating / hot water system boiler - Houses | Nr | 3600
6 | Radiators incl installation, valves and pipework - Apartments | Nr | 1625 | 6 | 9750 | 9 | 14625 | 9 | 14625 | 3 | 4875 | 4 | 6500
| Radiators incl installation, valves and pipework - Houses | Nr | 2925
7 | Small Power / Lighting installation | m2 | 80 | 388 | 31043 | 600 | 48000 | 600 | 48000 | 220 | 17565 | 260 | 20800
8 | Security / fire alarm / door entry / TV | Nr | 2600 | 6 | 15600 | 9 | 23400 | 9 | 23400 | 3 | 7800 | 4 | 10400
9 | Incoming service supplies to each unit | Nr | 2400 | 6 | 14400 | 9 | 21600 | 9 | 21600 | 3 | 7200 | 4 | 9600 | BT, Gas, Electrics, Water etc
10 | Lightning protection | It | Excluded |  | Excluded |  | Excluded |  | Excluded |  | Excluded |  | Excluded
11 | Cold water booster set | It | Excluded |  | Excluded |  | Excluded |  | Excluded |  | Excluded |  | Excluded
12 | PV installation | Nr | 2400 | 6 | 14400 | 9 | 21600 | 9 | 21600 | 3 | 7200 | 4 | 9600
13 | External lighting to entrances | It | 400 | 2 | 800 | 4 | 1600 | 4 | 1600 | 2 | 800 | 2 | 800
| Sub-Total |  |  |  | 139513 |  | 211105 |  | 211105 |  | 76220 |  | 93380
| M&E BWIC @ 5% |  |  |  | 6976 |  | 10555 |  | 10555 |  | 3811 |  | 4669
| Trade Contract Preliminaries @ 5% |  |  |  | 6976 |  | 10555 |  | 10555 |  | 3811 |  | 4669
| Total to Summary |  |  |  | 153465 |  | 232216 |  | 232216 |  | 83842 |  | 102718

## 6 External Works
6 External Works - Blocks A-E
Ref | Description | Unit | Rate | Qty | Total | Comments
1 | Soft Landscaping/Planting | It |  |  | 28600
2 | Areas laid to grass incl imported top soil | m2 | 18 | 1063 | 19134
3 | Permeable block paving to parking bays | m2 | 120 | 435 | 52200
4 | Formation of hammerheads | It |  |  | 40000
5 | Street furniture (signage, benches etc) | It |  |  | 5000
6 | Combined trench for service connections | m | 160 | 100 | 16000
7 | Storm / Foul water drainage - Site wide storm / foul drains | m | 210 | 136 | 28560
| Manholes / inspection chambers | Nr | 1400 | 20 | 28000
| Connection to main drainage system | Nr | 3000 | 5 | 15000
8 | Sud Drainage | m2 | 170 | 105 | 17850
9 | Communal footpaths | m2 | 90 | 82 | 7344
10 | 1200mm high wall | m | 600 | 37 | 22200
11 | Boundary railings | m | 360 | 32 | 11520
12 | Fencing to rear of residential units | m | 110 | 136 | 14960
13 | EO gate | Nr | 140 | 2 | 280
14 | Paving slabs | m2 | 95 | 36 | 3420
15 | Communal bin / Bike Store | It | 9000 | 2 | 18000
16 | Individual bike / bin stores | Nr | 400 | 4 | 1600
17 | EV charging points incl BWIC / electric cables etc | Nr | 2800 | 31 | 86800
18 | Formation of new road surface incl sub-base | m2 | 140 | 506 | 70840
19 | Bio retention pond | it | 11000 | 12 | 132000
| Package Total |  |  |  | 619308
| Preliminaries |  |  |  | 86703
| OH&P |  |  |  | 42361
| To Summary |  |  |  | 748400

## 6 Site Wide Works
6 Site Wide Works
Ref | Description | Rate | Unit | Qty | Total | Comments
1 | Divert existing drainage including reinstating carriageway - Traffic management |  | It |  | 20000 | Provisional Allowance
| Storm | 450 | m | 74 | 33300
| Foul | 450 | m | 74 | 33300
2 | New access road to rear of Block E | 140 | m2 | 390 | 54600
3 | Post and rail fence | 68 | m | 80 | 5440 | Provisional allowance
4 | 1.8m high boundary wall | 68 | m | 739 | 50252
| Package Total |  |  |  | 196892
| Preliminaries |  |  |  | 27565
| OH&P |  |  |  | 13467
| To Summary |  |  |  | 237900

## Design Information
6.1 Design Drawings & Information
Drwg Nr | Rev | Title
2316 - 010 | B | Block A Floor Plans
2316 - 011 | B | Block A Elevations
2316 - 012 | B | Block B Floor Plans
2316 - 013 | B | Block B Floor Plans
2316 - 014 | B | Block B Elevations
2316 - 015 | C | Block C Ground Floor Plans
2316 - 016 | C | Block C First and Second Floor Plans
2316 - 017 | B | Block C Elevations
2316 - 018 | C | Block D Floor Plans
2316 - 019 | C | Block D Elevations
2316 - 020 | C | Block D Elevations
2316 - 021 | C | Block E Floor Plans
2316 - 023 | A | Block E Elevations