## March 2026
ACTION RECOMMENDATIONS TO PC FOLLOWING SURVEY DD 06.10.25
Ref | Species | Survey notes | Recommendation | Work Priority | Date of Action | Cost
T034 | Common ash | Large cavity ground level north east facing. Compromised stem. Multi stemmed from 1m. Large secondary stem east facing at 1m is heavily leaning and weighed towards grass area. Secondary stems are heavily end weighted and heavily leaning. | Remove tree | 1 month | 2026-03-01 | £7,116 incl VAT
T043 | Ash | North east facing at ground level to 5m crack in stem. North west crack in stem with cavity detected behind. West facing at 5m old wound from failed limb. Limb is hanging in neighbouring tree. Major dead wood in canopy. | Remove tree | 1 month | 2026-03-01
G005 | Mixed species | Group of under story trees and shrubs. Dead leaning tree in group, tree has split in middle | Remove marked tree | 6 months | 2026-03-01
T012 | Fastigiate oak | Large lateral limb north facing at 1.5m has stretch marks in bark on side, limb is over-extented and heavily weighted towards road. East facing limb at 6m has tight union with included bark. Low canopy. | Reduce lateral spread of canopy by up to 3m | 6 months | 2026-03-01
T022 | Fastigiate oak | Large lateral limb north facing at 3m, large over-extended lateral limb south west facing at 2m. Epicormic growth in canopy. North west facing at 2 to 3m old historical woulnd in stem. | Reduce lateral spread of canopy by up to 3 to 4m to suitable live growth | 6 months | 2026-03-01
T029 | Fastigiate oak | Tree is growing on boundary with field. South east facing at ground level. Small wound in stem with cavity behind. Major deadwood throughout canopy. Evidence of previous failure west facing at 5m. Large over extended lateral limb north east facing at 10m, limb has fiber buckling at union. Tree canopy grows over basketball court. | Dead wood (major greater than 25mm). Reduce canopy up to 3m suitable live growth | 6 months | 2026-03-01
T030 | Fastigiate oak | North east facing at ground level large cavity in base of tree, cavity is approximately 40 tp 50cm deep with decay behind. South east facing at ground level cavity under base of trees connects with cavity south west fqcing. North west facing from 50cm tp 5m large wound in ste; with exposed heart wood and decay major dead wood in canopy. Low canopy over grass area. | Reduce canopy by up to 4m to suitable live growth | 6 months | 2026-03-01
T031 | Common ash | West facing at ground level olds failure at base of tree. Decay behind. Remaining stem has been compromised. | Remove tree | 6 months | 2026-03-01
T033 | Pendinculate oak | South west facing at ground level wound in stem with cavity behind. Evidence of old fungal bracket south west facing at 50cm. Major dead wood in canopy. Tree is in decline with stag heading. South facing at 8m woodpecker hold in lateral limb. Woodpecker hole on lateral limb south west facing at 4m | Dead wood (major greater than 25mm). Reduce canopy by up to 5m to suitable live growth | 6 months | 2026-03-01
T037 | Horse chestnut | Tree is multi stemmed from 1m. Main union is poor with included bark. Exposed surface roots. Tree is within in Forest School aread. | Reduce by 3m | 6 months | 2026-03-01
T038 | Horse chestnut | Tree is growing in Forest School area. North east facing at 1.5m cavity in top of stem with large lateral limb growing from site. Lateral limbs are heavily end weighted. | Reduce canopy by 5m to live growth | 6 months | 2026-03-01
T006 | Leyland cypress | Ivy on stem and in canopy. Multi-stemmed from 0.5m. Stems closest to road have heavily weighted limbs towards road. Main union has is included bark. Crossing and rubbing branches throughout canopy. | Remove tree | 1 year | 2026-03-01

## End 2026 - Early 2027
ACTION RECOMMENDATIONS TO PC FOLLOWING SURVEY DD 06.10.25
Ref | Species | Survey notes | Recommendation | Work Priority | Date of Action | Cost
T002 | Sycamore | Tree is growing on bank between road and village hall. Epicormic growth at base of stem. Canopy of tree is rubbing on roof. Over extended canopy south west facing. Tree is rubbing on BT lines | Reduce canopy by 2m. Clear structure by 2m | 1 year
T006 | Leyland cypress | Ivy on stem and in canopy. Multi stemmed from 0.5m. Main union has included bark. Crossing and rubbing branches throughout canopy. | Remove tree | 1 year
T007 | Whitebeqm | Twin stemmed from 5m. Large heavily end weighted lateral limbs south facing at 2m, east facing at 2m, North facing at 3m. Minor dead wood in canopy. Canopy is touching building. | Reduce canopy by 2m | 1 year
T013 | Silver birch | Tree is twin stemmed from ground level, stems are touching to 0.5m. Main stem is leaning and weighted North east facing, main stem is leaning and weighted south east facing. | Reduce secondary stem by u to 3m, reduce canopy over road by 2m, shape remaing canopy to match. | 1 year
T016 | Pedunculate oak | Tree has had large recent failure North facing, remainging stem has been compromised. | Remove tree | 1 year
T017 | Silver birch | Tree is twin stemmed from 6m. Heavily weighted lower canopy North facing over road. Secondary stem over road has possible area of decay at union. | Reduce canopy over road by 2m and reduce height of secondary stem by 2 to 3m. Aerial inspection of possible cavity above union. | 1 year
T020 | Common lime | Tree is twin stemmed from 2m. Main union is tight with included bark. Tight unions with included bard throughout tree | Pollard tree to approximately 10m | 1 year
T028 | Silver birch | Tree is heavily leaning and weighted south east facing towards grass area. | Reduce canopy by 3m | 1 year
T036 | Fastigiate oak | Thick under story making inspection difficult. South west facing at 8m old wound in stem with decay behind. Tree has been hevily reduced in the past. Dead wood in canopy. Tree grows over forest school area. | Reduce canopy by 2m. Reduce main stem above decayed center by 3m to lateral limb. Dead wood (major greater than 25mm) | 1 year
T044 | Bird cherry | Ivy covered stem. Twin stemmed from 5m. Large lateral limb North west facing at 2m. Canopy is heavily biased North east facing. | Reduce lateral spread by 2m | 1 year
T045 | Bird cherry | Multi stemmed from 1.5m heavily leaning and weighted east facing. Heavy fluting on stem | Reduce lateral spread by 3m | 1 year

## End 2027 - Early 2028
ACTION RECOMMENDATIONS TO PC FOLLOWING SURVEY DD 06.10.25
Ref | Species | Survey notes | Recommendation | Work Priority | Date of Action | Cost
T005 | Leyland cypress | Ivy on stem and in canopy. Multi stemmed from 0.5m. Stems closest to road have heavily weighted limbs towards road. Main stem has been reduced in the past. Canopy is rubbing on power line. | Remove tree | 2 years
T008 | Common lime | Twin stemmed from 8m, tight main union. Epicormic growth throughout canopy. Canopy extends over road. Old pruning wounds throughout canopy. | Reduce by 2 to 3m | 2 years
T010 | Silver birch | Tree is heavily leaning and weighted North facing. Large lateral limb North facing at 3m and north east facing at 6m are heavily weighted over road. | Reduce by 2m | 2 years
T015 | Silver birch | Weighted canopy North facing. Twin leaders from 12m | Reduce canopy over road by 2m | 2 years
T018 | Silver birch | Tree canopy is heavily leaning and weighted over road. Tree has been supressed by neighbouring trees. | Remove tree | 2 years
T039 | Bird cherry | Multi stemmed from 1.5m. Side laterals are leaning and heavily end weighted. Tree is leaning north facing . Tree in forest school area. | Reduce lateral spread and height of secondary stems by up to 3m | 2 years
0