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	ACTION

	1.
	INTRODUCTION & APOLOGIES
	

	
	None.
	

	
	
	

	2.
	NOTES OF MEETING NO.4
	

	
	Notes of meeting No. 4 held on the 4th December were considered to be a fair and reasonable record without the need for any changes. 

	

	3.
	DESIGN & GEOTECHNICAL SURVEY UPDATE
	

	(a)
	Design:  
PFA Advised that the horizontal and vertical geometry and drainage was nearing completion to the point where first draft submissions could be made the week ending Friday 7th February 2020.  PFA advised that the length R3 to the northern tie-in of the A350 could have a speed limit of 60mph by increasing the superelevation from 3.5% to 5% which would then satisfy the DMRB GD109 for the proposed radius.

[bookmark: _GoBack]WC advised that they had received some of the AIP’s from the Structural Engineer but were seeking/awaiting further information.

WC advised that it would be helpful to have early site of the first draft of the highway specification and other associated reports.  PFA to provide accordingly. 

	









PFA

	(b)
	Geotechnical
PFA advised that the further geotechnical survey work to inform the solution for the length R1 to R2 is programmed to start week commencing 20th January.  The geotechnical company to carry out the work is Endeavour Drilling whom DH and the Structural Engineer have met on site with the Land Owner.  The findings from this further work are anticipated for late February, early March subject to the weather as some of the survey work falls within the River Biss flood plain. 

	

	4.
	TRAFFIC SIGNS
	

	
	WC handed over a marked-up copy of the proposed traffic signs with their comments and recommended X heights.  PFA to review/revise plans.  WC handed over a proposed LDS for Woodland Industrial Estate to be located between R3 and R2 southbound.  
WC confirmed that West Ashton Road currently has a speed limit of 50mph.

Atkins to forward standard details for signs and bollard applicable to the scheme.  At the roundabout the white ‘keep left’ arrow is integrated into the chevron board at the left hand end and is lit.  

Meeting agreed there were no changes required to the existing signs at Yarnbrook as a result of the YWARR.

	PFA




SB

	5.
	TRAFFIC CALMING OF OLD A350
	

	
	Following the in principle Agreement at the last meeting for the Old A350 to be converted to a country lane , the meeting discussed the options further and based on WC’s experience at Semington, it was concluded that the preferred approach was not to form a country lane but leave the road as is, subject to the following works:

1. Recover / resurface the footway
2. Clean out the highway drainage system
3. Remove redundant road signs
4. Remove cats eyes and backfill.

PFA to revise drawing and resubmit.

Meetings discussed the length north of the existing West Ashton crossroads which is to be landscaped and concluded for the moment the works would remain as per the planning scheme until WC has considered their options further.  

	









PFA

WC


	6.
	ACCOMMODATION WORKS
	

	
	DH advised the meeting of the outcome of the site meeting with the Land Owner and the following changes to the scheme are required. 

1. Field access on the north side of the proposed A363 (R1 to R2) to be relocated to be opposite the field access adjacent to Bridge 2.  PFA advised that this was acceptable subject to any implications on flood risk that need further consideration.
2. Add field access to the proposed A350 south of roundabout R2.
3. Proposed field access adjacent to Bridge 2 to be split at the toe of the ramp to serve both land ownerships.  Ditch to be culverted. 
4. North of R3 add a field access to the east and move the proposed field access to align with it. 
5. At R2 add 100mm ducts across western and southern arms for private water supplies (gravity and pump), and to the east of R3.
6. Meeting agreed underpass No. 4 can be used to aid the movement of animals, however fencing to be such that animals to not have a ready access to the highway.

PFA to prepare separate plan for onward submission to the Land Owner by PHW. 

	















PFA

	7. 
	CONSTRUCTION PHASING
	

	
	Meeting discussed the construction phasing which would be dependent on the outcome of the further geotechnical survey and possible allowing R1 to R2 to be delayed for settlement. 

KR to forward his traffic management notes for further consideration.

Meeting agreed an invitation should be sent to the streetworks team for them to attend the next meeting. PFA to make initial contact and provide scheme plan. 

	


KR

PFA

	9.
	TENDERING
	

	
	Meeting discussed the tender process which is to be co-ordinated by PHW.  The value of the works will be well over the OJ threshold.  PHW to decide whether they go down the route of restricted tender list or an open tender list, probably the former. Getting tender prices in was a key part of informing the Business Case.  

	DH

	10.
	BUSINESS CASE
	

	
	TP outlined the current programme for preparing the Business Case and the work that needed to be done in readiness for the LEP submission which is critical to securing the monies.  In essence, it would be a 3 stage preparation and the LEP had advised that Atkins could use the Wiltshire Strategic Model. 

WC raised the possibility that the land for the YWARR would need to be owned by the applicant, ie not under option if the LEP were to release the monies.  DH to check as this has other implications, ie Outline Planning Consent to be drawn down which in turn means Section 106 negotiations need to be completed.  All recognise that the information must be ready for the Business Case. 

	TP




DH

	11.
	PROGRAMME
	

	
	Meeting discussed the programme and whilst the overall dates remain unchanged, what is clear is the programme is very tight and requires all concerned to focus on getting the Business Case through the LEP.  

	ALL

	12.
	ANY OTHER BUSINESS
	

	
	1. WC to advise what the specification for the wildflower seed mix will be.
2. PFA will prepare drainage reports to submit with the forthcoming plans.
3. PHW/WC to continue to investigate proposed planning consent and how the conditions can ‘break’ the YWARR from the residential ie a commencement of development. 
4. PFA to investigate any requirements as regards archaeology within the EIA relating to the YWARR. 
5. PFA to forward copies of approved plans for the improvement scheme to West Ashton Road linked to Leap Gate.  Meeting agreed it was practical for those works to form part of YWARR, but need to review how it is funded; also length R3 to crossroads can be deleted as this length will have reduced traffic.

	WC
PFA
PHW/WC


PFA

	13.
	DATE OF NEXT MEETING
	

	
	The date of the next meeting is 12 February 2020 at 1pm at Atkins. 
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